## Cover
Media plan for the event 2026
Daniil Pustovalov · dpustovalov.com
A form for a forum, conference, festival or opening: three phases of promotion, channels with coverage, second-by-second day X and analysis after.
Release date: April 2026
License: CC BY 4.0 - use, add to, do not claim as your own without a link.
What's inside
• Phases | What we do in 8 weeks, in a week and on day X
• Channels | Coverages, registrations, cost of participation
• Calendar | Weekly activity schedule
• Day X | What do we publish and when, right on the day of the event?
• After | Analysis: profitability, content, what to repeat
How to fill out
The gray cells are an example, rewrite them to suit your needs. Key fields are highlighted in yellow.

## Phases
The phases are fixed first: without them, the channels below turn into a list for the sake of a list.
Phase | Problem | What are we launching? | Acceptance metric
Announcement, 8-6 weeks in advance | Collect the first wave of registrations | Post in your channels, mail out to the database, landing page with the program | 30% of the registration plan
Acceleration, in 5-2 weeks | Get an audience for a fee | Target by interests and geo, sponsored posts, speakers repost | 80% of the registration plan
C'mon, last week | Bring registered people to the entrance | Messenger reminders, directions, letters 24 hours in advance and 2 hours in advance | Profitability ≥ 55%
Day X | Content straight from the site | Stories, short videos, quotes from speakers, photos of the hall | Day coverage ≥ announcement coverage
After, 1-2 weeks | Harvest | Recording, photo report, survey, offer for the next event | Applications after ≥ 10% of arrivals

## Channels
The first two lines almost always give the cheapest registration. We need to start with them.
Channel | Budget | Coverage | Transitions | Registration | Registration fee | Responsible
Your own channels and newsletter | 0
Speakers and partners | 0
VK Ads targeting by geo
Telegram Ads
Seeding in thematic channels
Posters and event aggregators
Outdoors near the site
Total

## Calendar
The numbers below are an example for guidance, not a benchmark. Rewrite it to fit your budget.
Week | Activity | Channel | Readiness of materials
-8 | Publication of the program and opening of registration | Landing page, your channels | Landing page, 3 texts
-7 | Announcement of speakers, one per day | Social networks, newsletter | Photos and bio of speakers
-6 | Start of paid traffic | VK Ads, Telegram Ads | 5 creatives, 2 offers
-4 | Seedings and partner announcements | Thematic channels | Ready post for partners
-2 | Early price closes | All channels | Deadline banner
-1 | Pressure and logistics | Messenger, letters | Map, timing, checklist
0 | Event day | Online broadcast and stories | Shooting plan
+1 | Photo report, recording, survey | Newsletter, social networks | Materials from the shooting

## Day X
The plan for the day is written in advance. There will be no time to come up with ideas on set.
Time | What we publish | Where | Who's filming
In 2 hours | Reminder with card and time code | Messenger | —
Start | The first photo of the hall, “we have started” | Stories | Photographer
Each report | One speaker quote card | Social networks | Content Manager
Break | Audience survey in stories | Stories | SMM
Final | Group photo, thanks | All channels | Photographer

## After
To be completed within a week after the event, while details are still remembered.
Indicator | Meaning | Output to the next event
Registrations
Got it
Profitability, %
Cost of what came
Applications after the event
Cheapest channel
Most expensive channel